{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Sheet0"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet0","index":0,"n_rows":51,"n_cols":36,"rows_kept":51,"cut":false,"hidden":false,"merged":[[0,0,0,35],[1,3,1,5],[1,6,1,7],[1,9,1,11],[1,13,1,15],[1,20,1,22],[1,23,1,25],[1,26,1,28],[1,29,1,31],[1,32,1,34],[1,18,1,19],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,8,2,8],[1,12,2,12],[1,16,1,17]],"flags":["formulas_cached_only"]}
["결과 목록"]
["시설물번호","시설물점검유형","점검주체","분류","","","시설/설비","","소재지","안전점검","","","진행상태","점검자","","","보수보강",null,"현지시정",null,"확보예산","","","추가확보추진예산","","","이후확보추진예산","","","소요예산","","","시설물 관리자","",""]
["","","","주관기관","점검대상 유형","대상","소유","시설명","","점검일자","점검방법","완료예정시기","","점검자_공무원","점검자_전문가","점검자_기타","지적사항","진행사항","지적사항","진행사항","국비","지방비","기타","국비","지방비","기타","국비","지방비","기타","국비","지방비","기타","이름","부서","대표전화번호","점검결과번호"]
["16130000126631","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울신림1단지아파트 101동","서울특별시 관악구 광신길 160","20220915~20220915","합동점검","2023년 이후","차년도 이후 조치예정","","이기수,장호룡,정상철,박한성","이세호,김동환","외벽 균열 보수 등","차년도 이후 조치예정","지하주차장 채광창 상부구간 청소 미흡 등 38건","조치완료","0","0","0","0","0","0","0","0","3,000,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126632","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울신림1단지아파트 102동","서울특별시 관악구 광신길 160","20220915~20220915","합동점검","2023년 이후","차년도 이후 조치예정","","이기수,장호룡,정상철,박한성","이세호,김동환","지붕 아스팔트 싱글 들뜸 보수 등 2건","차년도 이후 조치예정",null,"","0","0","1,000,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126633","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울신림1단지아파트 103동","서울특별시 관악구 광신길 160","20220915~20220915","합동점검","","점검완료","","이기수,장호룡,정상철,박한성","이세호,김동환","외벽 균열 보수 등","차년도 이후 조치예정",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126634","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울신림1단지아파트 104동","서울특별시 관악구 광신길 160","20220915~20220915","합동점검","2023년 이후","차년도 이후 조치예정","","이기수,장호룡,정상철,박한성","이세호,김동환","지하주차장 트렌치구간 콘크리트 박락","차년도 이후 조치예정",null,"","0","0","0","0","0","0","0","0","1,000,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126635","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울신림1단지아파트 105동","서울특별시 관악구 광신길 160","20220915~20220915","합동점검","","점검완료","","이기수,장호룡,정상철,박한성","이세호,김동환","외벽 균열 보수 등","차년도 이후 조치예정",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126636","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울신림1단지아파트 106동","서울특별시 관악구 광신길 160","20220915~20220915","합동점검","","점검완료","","이기수,장호룡,정상철,박한성","이세호,김동환","외벽 균열 보수 등","차년도 이후 조치예정",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126637","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울신림1단지아파트 107동","서울특별시 관악구 광신길 160","20220915~20220915","합동점검","","점검완료","","이기수,장호룡,정상철,박한성","이세호,김동환","외벽 균열 보수 등","차년도 이후 조치예정",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126638","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울등촌7 701동","서울특별시 강서구 공항대로43길 104","20220915~20220915","합동점검","2023년 이후","차년도 이후 조치예정","","이기수,장호룡,정상철,박한성","이세호,김동환","내력벽 균열보수 등","차년도 이후 조치예정","장애인경사로 램프구간 핸드레일 촉지판 미부착 등 38건","차년도 이후 조치예정","0","0","0","0","0","0","0","0","3,000,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126639","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울등촌7 702동","서울특별시 강서구 공항대로43길 104","20220915~20220915","합동점검","","점검완료","","이기수,장호룡,정상철,박한성","이세호,김동환","외벽 발코니 하부 물끊기 홈 철근노출","차년도 이후 조치예정",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126640","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울등촌7 703동","서울특별시 강서구 공항대로43길 104","20220915~20220915","합동점검","","점검완료","","이기수,장호룡,정상철,박한성","이세호,김동환",null,"",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126641","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울등촌7 704동","서울특별시 강서구 공항대로43길 104","20220915~20220915","합동점검","2023년 이후","차년도 이후 조치예정","","이기수,장호룡,정상철,박한성","이세호,김동환","4동주변 어린이 놀이시설 손잡이 커버 탈락 보수","차년도 이후 조치예정",null,"","0","0","0","0","0","0","0","0","200,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126642","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울등촌7 705동","서울특별시 강서구 공항대로43길 104","20220915~20220915","합동점검","2023년 이후","차년도 이후 조치예정","","이기수,장호룡,정상철,박한성","이세호,김동환","옥탑층 승강기실 외벽 철근노출 보수","차년도 이후 조치예정",null,"","0","0","0","0","0","0","0","0","500,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126643","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","서울등촌7 706동","서울특별시 강서구 공항대로43길 104","20220915~20220915","합동점검","","점검완료","","이기수,장호룡,정상철,박한성","이세호,김동환","외벽 발코니 하부 물끊기 홈 철근노출","차년도 이후 조치예정",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126644","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","인천부개5단지아파트 511동","인천광역시 부평구 부개로 11","20220914~20220914","합동점검","2022년 12","조치완료","이지관","이동윤,정상철,장호룡,박한성","이세호,김동환","승강기 기계실 외벽 크랙(다수), 지하주차장 B2F 상부 거더 균열보수, 지하주차장 B2F 프리액션밸브실 앞 천정 누수 등","조치완료","지하저수조 내부 철재계단 등받이 사다리 설치 등 66건","조치완료","0","0","11,658,600","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","3"]
["16130000126645","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","인천부개5단지아파트 512동","인천광역시 부평구 부개로 11","20220914~20220914","합동점검","2022년 12","조치완료","이지관","이동윤,정상철,장호룡,박한성","이세호,김동환","동 출입구 천정 누수, 20층 프리액션밸브실 천정 누수, 옥상 방수층 들뜸 등","조치완료",null,"","0","0","4,092,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126646","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","인천부개5단지아파트 513동","인천광역시 부평구 부개로 11","20220914~20220914","합동점검","2022년 12","조치완료","이지관","이동윤,정상철,장호룡,박한성","이세호,김동환","옥상 A라인 방수층 들뜸 등","조치완료",null,"","0","0","11,484,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126647","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대전판암3 301동","대전광역시 동구 옥천로 152-9","20220921~20220921","합동점검","2023년 이후","차년도 이후 조치예정","박대종","이기수,장호룡,정상철,김원봉","이세호,김동환","복도창호 상부 균열 보수 등 2건","차년도 이후 조치예정","옥상방화문 후레임 부식발생 등 17건","조치중","0","0","0","0","0","0","0","0","1,000,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126648","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대전판암3 302동","대전광역시 동구 옥천로 152-9","20220921~20220921","합동점검","2023년 이후","차년도 이후 조치예정","박대종","이기수,장호룡,정상철,김원봉","이세호,김동환","복도창호 상부 균열 보수 등 2건","차년도 이후 조치예정","옥상방화문 후레임 부식발생 등 17건","차년도 이후 조치예정","0","0","0","0","0","0","0","0","1,000,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126649","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대전판암3 303동","대전광역시 동구 옥천로 152-9","20220921~20220921","합동점검","2023년 이후","차년도 이후 조치예정","박대종","이기수,장호룡,정상철,김원봉","이세호,김동환","복도창호 상부 균열 보수 등 1건","차년도 이후 조치예정","옥상방화문 후레임 부식발생 등 16건","차년도 이후 조치예정","0","0","0","0","0","0","0","0","500,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126650","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대전구봉마을8-2아파트 815동","대전광역시 서구 관저로 84","20220921~20220921","합동점검","2023년 이후","차년도 이후 조치예정","박대종","이기수,장호룡,정상철,김원봉","이세호,김동환",null,"","E/V 입구 장애인 점자블럭 미설치 등 12건","차년도 이후 조치예정","0","0","0","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126664","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대전구봉마을8-2아파트 816동","대전광역시 서구 관저로 84","20220921~20220921","합동점검","","점검완료","박대종","이기수,장호룡,정상철,김원봉","이세호,김동환",null,"",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126651","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대전구봉마을8-2아파트 817동","대전광역시 서구 관저로 84","20220921~20220921","합동점검","2023년 이후","차년도 이후 조치예정","박대종","이기수,장호룡,정상철,김원봉","이세호,김동환",null,null,"E/V 입구 장애인 점자블럭 미설치 등 13건","조치완료","0","0","0","0","0","0","0","0","1,000,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126652","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대전구봉마을8-2아파트 818동","대전광역시 서구 관저로 84","20220921~20220921","합동점검","2023년 이후","차년도 이후 조치예정","박대종","이기수,장호룡,정상철,김원봉","이세호,김동환","주차장 출입구 Ramp구간 누수발생 등 2건","차년도 이후 조치예정","E/V 입구 장애인 점자블럭 미설치 등 12건","차년도 이후 조치예정","0","0","0","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126653","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대전구봉마을8-2아파트 819동","대전광역시 서구 관저로 84","20220921~20220921","합동점검","2023년 이후","차년도 이후 조치예정","박대종","이기수,장호룡,정상철,김원봉","이세호,김동환","주변 어린이놀이터 출입구 단차보수 등","차년도 이후 조치예정","E/V 입구 장애인 점자블럭 미설치 등 12건","차년도 이후 조치예정","0","0","0","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126665","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대전구봉마을8-2아파트 820동","대전광역시 서구 관저로 84","20220921~20220921","합동점검","","점검완료","","이기수,장호룡,정상철,김원봉","이세호,김동환",null,"",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126654","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","천안쌍용5-2 517동","충청남도 천안시 서북구 봉서산샛길 64","20220920~20220920","합동점검","2023년 이후","차년도 이후 조치예정","박대종","이기수,장호룡,정상철,김원봉","이세호,김동환","지붕층 아스팔트 슁글 접합부 들뜸 등 3건","차년도 이후 조치예정","재활용 분리수거장 소화기 비치 필요 등 15건","조치완료","0","0","0","0","0","0","0","0","1,500,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126655","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","천안쌍용5-2 518동","충청남도 천안시 서북구 봉서산샛길 64","20220920~20220920","합동점검","2023년 이후","차년도 이후 조치예정","박대종","이기수,장호룡,정상철,김원봉","이세호,김동환","지붕층 아스팔트 슁글 접합부 들뜸 등 3건","차년도 이후 조치예정","재활용 분리수거장 소화기 비치 필요 등 15건","차년도 이후 조치예정","0","0","0","0","0","0","0","0","1,500,000","","","","김동환","자산안전관리단","055-922-4219","2"]
["16130000126656","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","천안쌍용5-2 519동","충청남도 천안시 서북구 봉서산샛길 64","20220920~20220920","합동점검","2023년 이후","차년도 이후 조치예정","박대종","이기수,장호룡,정상철,김원봉","이세호,김동환","지붕층 아스팔트 슁글 접합부 들뜸 등 2건","차년도 이후 조치예정","재활용 분리수거장 소화기 비치 필요 등 15건","차년도 이후 조치예정","0","0","0","0","0","0","0","0","1,000,000","","","","김동환","자산안전관리단","055-922-4219","2"]
["16130000126660","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","광주운남1단지아파트 101동","광주광역시 광산구 목련로273번길 76","20220929~20220929","합동점검","2023년 이후","차년도 이후 조치예정","","이준수,장호룡,장상철,홍정화","이세호,김동환","101동 옥탑 옥상 방수파손 외8건","차년도 이후 조치예정","엘리베이터 주변 점검구 출입문 잠금조치외 63건","차년도 이후 조치예정","0","0","30,000,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","3"]
["16130000126661","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","광주운남1단지아파트 102동","광주광역시 광산구 목련로273번길 76","20220929~20220929","합동점검","2023년 이후","차년도 이후 조치예정","","이준수,장호룡,정상철,홍정화","이세호,김동환","현관 출입구(전면)낙하물 방지망 관리요함","차년도 이후 조치예정","소방 연결 송수구 허용압력 미표시 외2건","차년도 이후 조치예정","0","0","3,000,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","2"]
["16130000126662","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","광주운남1단지아파트 103동","광주광역시 광산구 목련로273번길 76","20220929~20220929","합동점검","2023년 이후","차년도 이후 조치예정","","이준수,장호룡,정상철,홍정화","이세호,김동환","현관 출입구(전면) 낙하물 방지망 설치 요함","차년도 이후 조치예정","승강기 기계실 소화기 비치 관리 요함 외1건","차년도 이후 조치예정","0","0","3,000,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","2"]
["16130000126663","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","광주운남1단지아파트 104동","광주광역시 광산구 목련로273번길 76","20220929~20220929","합동점검","2023년 이후","차년도 이후 조치예정","","이준수,장호룡,정상철,홍정화","이세호,김동환","현관 출입구(전면)낙하물 방지망 설치 요함","차년도 이후 조치예정","지하 방화문 도어클로저 연결 관리 요함 외2건","차년도 이후 조치예정","0","0","3,000,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","2"]
["16130000126670","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","목포연산1 101동","전라남도 목포시 원산중앙로 108","20220929~20220929","합동점검","2023년 이후","차년도 이후 조치예정","","이준수,장호룡,정상철,홍정화","이세호,김동환","복도 세대외벽 균열발생(창틀,전결계주위 등)외 5건","차년도 이후 조치예정","비상계단 15층 슬라브 누수흔정 발생 외43건","차년도 이후 조치예정","0","0","30,000,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126671","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","목포연산1 102동","전라남도 목포시 원산중앙로 108","20220929~20220929","합동점검","2023년 이후","차년도 이후 조치예정","","이준수,장호룡,정상철,홍정화","이세호,김동환","외벽 실외가 측벽 파손 및 콘크리트 박락 발생 외4건","차년도 이후 조치예정","후면 주차장 진출입 관리 사각지대 발생(CCTV추가필요)","차년도 이후 조치예정","0","0","5,000,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126672","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","목포연산1 103동","전라남도 목포시 원산중앙로 108","20220929~20220929","합동점검","2023년 이후","차년도 이후 조치예정","","이준수,장호룡,정상철,홍정화","이세호,김동환","9층 베란다측 물끊기홈 철근노출 보수요함","차년도 이후 조치예정","승강기 기계실 환풍기 작동불량/내부열 방출미비","차년도 이후 조치예정","0","0","3,000,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126673","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","목포연산1 104동","전라남도 목포시 원산중앙로 108","20220929~20220929","합동점검","2023년 이후","차년도 이후 조치예정","","이준수,장호룡,정상철,홍정화","이세호,김동환","복도5~6충,베란다측10~12층 콘크리트 박락 보수요함","차년도 이후 조치예정",null,"","0","0","3,000,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126674","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대구성서3주공아파트 301동","대구광역시 달서구 신당로 55","20220922~20220922","합동점검","2023년 이후","차년도 이후 조치예정","이지관","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완","지하층 피트 트랜치 커버뒤틀림 이완 외 2건","차년도 이후 조치예정","준비작동식밸브실 적치물 제거 등","차년도 이후 조치예정","0","0","0","0","0","0","0","0","8,000,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126675","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대구성서3주공아파트 302동","대구광역시 달서구 신당로 55","20220922~20220922","합동점검","2023년 이후","차년도 이후 조치예정","이지관","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완","복도별 균열 발생(창호 ,계량기 등) 외 1건","차년도 이후 조치예정","계단통로유도표지 축광기능 상실 등","차년도 이후 조치예정","0","0","0","0","0","0","0","0","2,500,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126676","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대구성서3주공아파트 303동","대구광역시 달서구 신당로 55","20220922~20220922","합동점검","2023년 이후","차년도 이후 조치예정","이지관","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완","복도벽 균열 발생(창호, 계량기 등 주위) 외 1건","차년도 이후 조치예정","계단통로유도표지 축광기능 상실 등","차년도 이후 조치예정","0","0","0","0","0","0","0","0","2,500,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126677","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대구성서3주공아파트 304동","대구광역시 달서구 신당로 55","20220922~20220922","합동점검","2023년 이후","차년도 이후 조치예정","이지관","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완","현관 낙하물 방지망","차년도 이후 조치예정","계단통로유도표지 축광기능 상실 등","차년도 이후 조치예정","0","0","0","0","0","0","0","0","2,100,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126678","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","대구성서3주공아파트 305동","대구광역시 달서구 신당로 55","20220922~20220922","합동점검","2023년 이후","차년도 이후 조치예정","이지관","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완","외벽 박리(주의관찰) 외 1건","차년도 이후 조치예정","계단통로유도표지 축광기능 상실 등","차년도 이후 조치예정","0","0","0","0","0","0","0","0","2,100,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126679","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","구미인의 아파트 201동","경상북도 구미시 인동16길 48-1","20220922~20220922","합동점검","2022년 12","조치완료","","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완","옥상지붕바닥 균열발생 및 물탱크 외벽 균열발생","차년도 이후 조치예정","계단 유도등 건전지 교체 등","조치완료","0","0","1,000,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126680","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","구미인의 아파트 202동","경상북도 구미시 인동16길 48-1","20220922~20220922","합동점검","2023년 이후","차년도 이후 조치예정","","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완","지하층 균열 외 2건","조치완료","준비작동식밸브실 적치물 제거 등","조치완료","0","0","0","0","0","0","0","0","3,000,000","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126681","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","구미인의 아파트 203동","경상북도 구미시 인동16길 48-1","20220922~20220922","합동점검","","점검완료","","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완",null,"",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126682","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","구미인의 아파트 204동","경상북도 구미시 인동16길 48-1","20220922~20220922","합동점검","","점검완료","","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완",null,"",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126683","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","구미인의 아파트 205동","경상북도 구미시 인동16길 48-1","20220922~20220922","합동점검","","점검완료","","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완",null,"",null,"","","","","","","","","","","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126684","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","구미인의 아파트 206동","경상북도 구미시 인동16길 48-1","20220922~20220922","합동점검","2022년 12","조치완료","","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완","지붕 방수층 파손 및 지하주차장 트랜치커버 단차발생","조치완료","준비작동식밸브실 적치물 제거 등","조치완료","0","0","1,000,000","0","0","0","0","0","0","","","","김동환","자산안전관리단","055-922-4219","1"]
["16130000126685","부처직접수행","국토교통부 한국토지주택공사","국토교통부","건축시설","공동주택","공공","구미인의 아파트 207동","경상북도 구미시 인동16길 48-1","20220922~20220922","합동점검","2023년 이후","차년도 이후 조치예정","","이준수,김원봉,정상철,장호룡","이세호,김동환,김태완","동입구 낙하물 방지망","조치완료","준비작동식밸브실 적치물 제거 등","조치완료","0","0","0","0","0","0","0","0","2,000,000","","","","김동환","자산안전관리단","055-922-4219","1"]