{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["Sheet1","Sheet2"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":0,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":43,"n_cols":57,"rows_kept":43,"cut":false,"hidden":false,"merged":[[0,0,0,56],[2,0,2,29],[3,0,8,0],[4,26,8,26],[3,3,3,7],[4,8,4,9],[3,8,3,9],[4,28,4,29],[4,3,8,3],[3,2,8,2],[3,1,8,1],[4,22,8,22],[5,56,8,56],[3,54,3,56],[2,30,2,40],[4,43,6,47],[3,30,3,40],[2,41,2,56],[4,49,6,53],[4,31,8,31],[4,30,8,30],[4,54,8,54],[4,55,8,55],[4,42,8,42],[4,48,8,48],[7,43,7,47],[7,35,8,35],[7,34,8,34],[3,16,3,17],[4,5,8,5],[4,10,8,10],[3,41,3,53],[4,32,8,32],[6,34,6,40],[4,33,5,40],[4,21,8,21],[4,20,8,20],[4,27,8,27],[4,25,8,25],[4,24,8,24],[3,23,3,27],[3,19,8,19],[5,8,8,8],[5,9,8,9],[4,7,8,7],[4,6,8,6],[7,49,7,53],[7,36,7,40],[4,41,8,41],[1,1,1,12],[3,28,3,29],[5,28,8,28],[5,29,8,29],[3,11,3,15],[4,16,8,16],[3,20,3,22],[4,14,8,14],[4,13,8,13],[4,12,8,12],[4,11,8,11],[4,23,8,23],[4,15,8,15],[3,18,8,18],[4,17,8,17],[4,4,8,4]]}
["2026년 해빙기(우기) 급경사지 안전점검 결과(한국토지주택공사)"]
[null,"메뉴에 표출되는 '콘텐츠 사용' 클릭 후 작업 필요!!"]
["① 급경사지 안전점검 대상",{"$nulls":29},"② 안전점검",{"$nulls":10},"③ 후속 조치"]
["연번","급경사지명","관리번호","위    치",{"$nulls":4},"용도\n(비탈면 보호 목적)",null,"분류","제    원",{"$nulls":4},"관리기관",null,"인명피해 우려 급경사지 여부\n(선택 O, X)","주민대피 관리기준 여부\n(선택 O, X)","재해위험도평가",null,null,"붕괴위험지역",{"$nulls":4},"계측기",null,"점검결과",{"$nulls":10},"조치 현황(건)",{"$nulls":12},"조치 현황 중 \"미완료\" 건에 대한 조치계획"]
[null,null,null,"시·도","시.군.구","읍·면·동","리·동","지번","종류\n(선택)",null,"유형\n(선택)","구조\n(중복선택)","종단길이(m)","최고수직고(m)","평균경사(°)","붕괴이력","관리기관\n(선택)","공공/민간\n(선택)",null,null,"평가일자","평가점수","평가등급\n(선택)","위험등급\n(선택)","지정/해제 여부\n(선택)","지정일자","해제일자","위험해소\n방안(상세)","계측기 설치 여부\n(선택 O, X)",null,"안전점검일자(YY-MM-DD)","급경사지 정보시스템\n점검결과 입력일\n(YY-MM-DD)","점검 주요내용","안전점검결과(선택, 안전 : 지적 0개, 불안전 : 지적 1개 이상)",{"$nulls":7},"계\n(A+B)\n* 지적건수와 동일","완료(건)\n(A)",{"$nulls":5},"미완료(건)\n(B)",{"$nulls":5},"계(건)\n* 미완료 건수와 동일","조치 계획"]
[{"$nulls":9},"종류 중 \n기타 선택 시 \n상세작성",{"$nulls":19},"작동 여부\n(선택 O, X)",{"$nulls":26},"완료 예정일\n(~M월)"]
[{"$nulls":34},"안전점검결과 중 \"불안전\" 건에 대한 지젹 현황"]
[{"$nulls":34},"지적 건수(건)","지적내용","지적사항 조치계획(자동)",{"$nulls":6},"완료 현황(자동)",{"$nulls":5},"미완료 현황(자동)"]
[{"$nulls":37},"응급처치(선택)","보수보강계획(선택)","정밀조사 필요(선택)","긴급안전조치 필요(선택)",null,null,null,"응급처치(중복선택)","보수보강(중복선택)","정밀조사\n(선택)","긴급안전조치(선택)\n: 관계인 안전점검 결과 통보 등",null,null,"응급처치(중복선택)","보수보강계획(중복선택)","정밀조사\n(선택)","긴급안전조치(선택)\n: 관계인 안전점검 결과 통보 등"]
["총계",{"$f":"SUBTOTAL(3,B11:B981)","v":33},{"$nulls":6},{"$f":"SUBTOTAL(3,I11:I981)","v":33},null,{"$f":"SUBTOTAL(3,K11:K981)","v":33},{"$nulls":5},{"$f":"SUBTOTAL(3,Q11:Q981)","v":33},{"$f":"SUBTOTAL(3,R11:R981)","v":33},{"$f":"SUBTOTAL(3,S11:S981)","v":33},{"$f":"COUNTIF(T11:T1048576,\"O\")","v":33},null,null,{"$f":"SUBTOTAL(3,W11:W981)","v":33},{"$f":"SUBTOTAL(3,X11:X981)","v":33},{"$f":"SUBTOTAL(3,Y11:Y981)","v":33},null,null,null,{"$f":"COUNTIF(AC11:AC1048576,\"O\")","v":0},{"$f":"COUNTIF(AD11:AD1048576,\"O\")","v":0},null,null,null,{"$f":"COUNTIF(AH11:AH1048576,\"불안전\")","v":5},{"$f":"SUM(AI11:AI1048576)","v":5},null,null,{"$f":"COUNTIF(AL11:AL1048576,\"O\")","v":1},{"$f":"COUNTIF(AM11:AM1048576,\"O\")","v":4},{"$f":"COUNTIF(AN11:AN1048576,\"O\")","v":0},{"$f":"COUNTIF(AO11:AO1048576,\"O\")","v":0},{"$f":"AQ10+AW10","v":5},{"$f":"SUM(AQ11:AQ1048576)","v":0},null,null,null,{"$f":"COUNTIF(AU11:AU1048576,\"O\")","v":0},{"$f":"COUNTIF(AV11:AV1048576,\"O\")","v":0},{"$f":"SUM(AW11:AW1048576)","v":5},null,null,null,{"$f":"COUNTIF(BA11:BA1048576,\"O\")","v":0},{"$f":"COUNTIF(BB11:BB1048576,\"O\")","v":0},{"$f":"AW10","v":5}]
[1,"여수문수",4613000107,"전라남도","여수시","문수동",null,797,"아파트",null,"인공 비탈면","콘크리트옹벽",176,45,44,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-17","2026-03-17","배수로","불안전",1,"배수로 퇴적",{"$f":"_xlfn.TEXTJOIN(\", \", TRUE,\n IF(AL11=\"O\", LEFT($AL$9,4), \"\"),\n IF(AM11=\"O\", LEFT($AM$9,6), \"\"),\n IF(AN11=\"O\", LEFT($AN$9,7), \"\"),\n IF(AO11=\"O\", LEFT($AO$9,9), \"\")\n)","v":"응급처치"},"O","X","X","X",{"$f":"SUM(AW11,AQ11)","v":1},0,{"$f":"_xlfn.TEXTJOIN(\", \", TRUE,\n IF(AS11<>\"\", LEFT(AS$9,4), \"\"),\n IF(AT11<>\"\", LEFT(AT$9,6), \"\"),\n IF(AU11=\"O\", LEFT(AU$9,4), \"\"),\n IF(AV11=\"O\", LEFT(AV$9,6), \"\")\n)","v":""},{"$nulls":4},1,{"$f":"_xlfn.TEXTJOIN(\", \", TRUE,\n IF(AY11<>\"\", LEFT(AY$9,4), \"\"),\n IF(AZ11<>\"\", LEFT(AZ$9,4), \"\"),\n IF(BA11=\"O\", LEFT(BA$9,4), \"\"),\n IF(BB11=\"O\", LEFT(BB$9,6), \"\")\n)","v":"응급처치"},"배수로정비",null,null,null,1,"배수로 정비","~5월"]
[2,"여수소호",4613000108,"전라남도","여수시","소호동",null,"352-1","아파트",null,"인공 비탈면","콘크리트옹벽",264,7,66,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-17","2026-03-17",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW12,AQ12)","v":0},0]
[3,"담양백동1",4671000080,"전라남도","담양군","담양읍","댁동리",191,"아파트",null,"인공 비탈면","콘크리트옹벽",210,10,37,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-17","2026-03-17",null,"안전",0,null,null,"X","X","X","X",0,0]
[4,"울산구영2",3171000004,"울산광역시","울주군","범서읍","구영리","855-2","아파트",null,"인공 비탈면","석축옹벽",27,12,35,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-04-06","2026-04-06",null,"안전",0,null,null,"X","X","X","X",0,0]
[5,"울산구영1",3171000003,"울산광역시","울주군","범서읍","구영리",212,"아파트",null,"인공 비탈면","석축옹벽",215,8,45,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-04-06","2026-04-06",null,"안전",0,null,null,"X","X","X","X",0,0]
[6,"서울신림3",1162000109,"서울특별시","관악구","신림동",null,null,"아파트",null,"인공 비탈면","석축옹벽",54,7,"-","x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-04-06","2026-04-06",null,"안전",0,null,null,"X","X","X","X",0,0]
[7,"부산모라1",2653000060,"부산광역시","사상구","모라동",null,552,"아파트",null,"인공 비탈면","콘크리트옹벽",50,43,45,"x","한국토지주택공사","공공","O","O","-","-","C","A","해제","-","-",null,"X","X","2026-04-03","2026-04-03",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW17,AQ17)","v":0},0]
[8,"부산금곡4",2632000060,"부산광역시","북구","금곡동",null,1108,"아파트",null,"인공 비탈면","콘크리트옹벽",479,23,45,"x","한국토지주택공사","공공","O","O","-","-","C","A","해제","-","-",null,"X","X","2026-04-03","2026-04-03","균열","불안전",1,"균열 및 전도",null,"X","O","X","X",1,0,{"$nulls":5},1,null,null,"기타",null,null,1,"보수보강","~5월"]
[9,"부산모라1",2653000059,"부산광역시","사상구","모라동",null,552,"아파트",null,"인공 비탈면","콘크리트옹벽",50,43,45,"x","한국토지주택공사","공공","O","O","-","-","C","A","해제","-","-",null,"X","X","2026-04-03","2026-04-03","세굴","불안전",1,"기초 세굴",null,"X","O","X","X",{"$f":"SUM(AW19,AQ19)","v":1},0,{"$nulls":5},1,null,null,"기타",null,null,1,"보수보강","~5월"]
[10,"부산금곡1",2632000059,"부산광역시","북구","금곡동",null,"53-1","아파트",null,"인공 비탈면","콘크리트옹벽",155,12,35,"x","한국토지주택공사","공공","O","O","-","-","C","A","해제","-","-",null,"X","X","2026-04-03","2026-04-03","균열","불안전",1,"균열 및 전도",null,"X","O","X","X",{"$f":"SUM(AW20,AQ20)","v":1},0,{"$nulls":5},1,null,null,"기타",null,null,1,"보수보강","~5월"]
[11,"부산동삼1",2620000041,"부산광역시","영도구","동삼동",null,1121,"아파트",null,"인공 비탈면","콘크리트옹벽",250,12,35,"x","한국토지주택공사","공공","O","O","-","-","C","A","해제","-","-",null,"X","X","2026-04-03","2026-04-03",null,"안전",0,null,null,"X","X","X","X",0,0]
[12,"부산정관1",2671000112,"부산광역시","기장군","정관읍","용수리",1359,"아파트",null,"인공 비탈면","석축옹벽",266,12,45,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-04-06","2026-04-06",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW22,AQ22)","v":0},0]
[13,"부산정관2",2671000113,"부산광역시","기장군","정관읍","모전리",768,"아파트",null,"인공 비탈면","석축옹벽",415,5,45,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-04-06","2026-04-06",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW23,AQ23)","v":0},0]
[14,"부산고촌",2671000114,"부산광역시","기장군","철마면","고촌로",615,"아파트",null,"인공 비탈면","콘크리트옹벽",54,7,45,"x","한국토지주택공사","공공","O","O","-","-","C","A","해제","-","-",null,"X","X","2026-04-06","2026-04-06",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW24,AQ24)","v":1},0,{"$nulls":5},1,null,null,"기타",null,null,1,"보수보강","~5월"]
[15,"광주죽림",2917000034,"광주광역시","북구","동림동",null,234,"아파트",null,"인공 비탈면","콘크리트옹벽",188,13,57,"x","한국토지주택공사","공공","O","O","-","-","C","A","해제","-","-",null,"X","X","2026-03-31","2026-03-31","붕괴","불안전",1,"표층 붕괴",null,"X","O","X","X",{"$f":"SUM(AW25,AQ25)","v":0}]
[16,"광주신용",2917000036,"광주광역시","북구","신용동",null,647,"아파트",null,"인공 비탈면","콘크리트옹벽",229,10,35,"x","한국토지주택공사","공공","O","O","-","-","C","A","해제","-","-",null,"X","X","2026-03-24","2026-03-24",null,"안전",0,null,null,"X","X","X","X",0,0]
[17,"광주용두",2917000037,"광주광역시","북구","용두동",null,1089,"아파트",null,"인공 비탈면","콘크리트옹벽",81,9,61,"x","한국토지주택공사","공공","O","O","-","-","A","A","해제","-","-",null,"X","X","2026-03-24","2026-03-24",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW27,AQ27)","v":0},0]
[18,"도량1지구",4719000046,"경상북도","구미시","도량동",null,219,"아파트",null,"인공 비탈면","콘크리트옹벽",97,10,6,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-23","2026-03-23",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW28,AQ28)","v":0},0]
[19,"경산사동",4729000092,"경상북도","경산시","평산동",null,null,"아파트",null,"인공 비탈면","콘크리트옹벽",54,22,27,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-27","2026-03-27",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW29,AQ29)","v":0},0]
[20,"울릉저동",4794000057,"경상북도","울릉군","울릉읍","저동리",null,"아파트",null,"인공 비탈면","콘크리트옹벽",243,15,33,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-27","2026-03-27",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW30,AQ30)","v":0},0]
[21,"구미옥계2",4719000128,"경상북도","구미시","옥계동",null,905,"아파트",null,"인공 비탈면","석축옹벽",68,5,88,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-23","2026-03-23",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW31,AQ31)","v":0},0]
[22,"경산하양3",4729000229,"경상북도","경산시","하양읍","양지리",265,"아파트",null,"인공 비탈면","석축옹벽",120,3,85,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-26","2026-03-26",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW32,AQ32)","v":0},0]
[23,"대구금호5",2723000028,"대구광역시","북구","사수동",null,787,"아파트",null,"인공 비탈면","토사",300,8.5,36,"x","한국토지주택공사","공공","O","O","-","-","C","A","해제","-","-",null,"X","X","2026-03-16","2026-03-16",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW33,AQ33)","v":0},0]
[24,"진주평거2",4817000282,"경상남도","진주시","평거동",null,392,"아파트",null,"인공 비탈면","토사",70,5,35,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-31","2026-03-31",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW34,AQ34)","v":0},0]
[25,"마산중리",4812700166,"경상남도","창원시 마산회원구","내서읍","상곡리",193,"아파트",null,"인공 비탈면","토사",59,5,36,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-27","2026-03-27",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW35,AQ35)","v":0},0]
[26,"김해구산",4825000463,"경상남도","김해시","구산동",null,null,"아파트",null,"인공 비탈면","토사",110,6,38,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-27","2026-03-27",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW36,AQ36)","v":0},0]
[27,"거제장평",4831000097,"경상남도","거제시","장평동",null,"815-13","아파트",null,"인공 비탈면","콘크리트옹벽",45,5,35,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-20","2026-03-20",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW37,AQ37)","v":0},0]
[28,"의령서동",4872000297,"경상남도","의령군","의령읍","서동리",null,"아파트",null,"인공 비탈면","토사",99,5,34,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-27","2026-03-27",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW38,AQ38)","v":0},0]
[29,"성남도촌2",4113300014,"경기도","성남시","중원구","도촌동",701,"아파트",null,"인공 비탈면","콘크리트옹벽",80,12,45,"x","한국토지주택공사","공공","O","O","-","-","C","A","해제","-","-",null,"X","X","2026-03-10","2026-03-10",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW39,AQ39)","v":0},0]
[30,"성남도촌9",4113300014,"경기도","성남시","중원구","도촌동",709,"아파트",null,"인공 비탈면","콘크리트옹벽",154,10,63,"x","한국토지주택공사","공공","O","O","-","-","C","A","해제","-","-",null,"X","X","2026-03-10","2026-03-10",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW40,AQ40)","v":0},0]
[31,"소사주공2",4119000018,"경기도","부천시","소사구","소사본동","408-1","아파트",null,"인공 비탈면","콘크리트옹벽",148,12,90,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-31","2026-03-31",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW41,AQ41)","v":0},0]
[32,"의정부금오9",4115000036,"경기도","의정부시","신곡동",null,790,"아파트",null,"인공 비탈면","콘크리트옹벽",168,6,90,"x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-10","2026-03-10",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW42,AQ42)","v":0},0]
[33,"남양주퇴계원4",4136000201,"경기도","남양주시","별내면",null,366,"아파트",null,"인공 비탈면","콘크리트옹벽",239,8,"-","x","한국토지주택공사","공공","O","O","-","-","B","A","해제","-","-",null,"X","X","2026-03-10","2026-03-10",null,"안전",0,null,null,"X","X","X","X",{"$f":"SUM(AW43,AQ43)","v":0},0]

{"sheet":"Sheet2","index":1,"n_rows":15,"n_cols":13,"rows_kept":15,"cut":false,"hidden":true,"merged":[]}
["응급처치","보수보강계획","비탈면 용도","분류","비탈면 구조","관리기관","공공/민간","O/X","등급","지정/해제","안전/불안전","조치","공개 여부"]
["배수로정비","낙석방지망","도로","인공 비탈면","토사","지방자치단체","공공","O","A","지정","안전","응급처치","공개"]
["천막피복덮기","녹화석재","아파트","자연 비탈면","콘크리트옹벽","지방산림청","민간","X","B","해제","불안전","보수보강계획","비공개"]
["안전선 및 간판 설치","법면유실보호망","주택","산지","석축옹벽","한국농어촌공사",null,null,"C",null,null,"정밀조사"]
["마대쌓기","암반보강","공단",null,"암반","한국토지주택공사",null,null,"D",null,null,"긴급안전조치"]
["기타","기타","공원",null,"기타","국가철도공단",null,null,"E"]
[null,null,"학교",null,null,"서울교통공사"]
[null,null,"공공시설",null,null,"부산교통공사"]
[null,null,"사유시설",null,null,"인천교통공사"]
[null,null,"기타",null,null,"대구교통공사"]
[{"$nulls":5},"대전교통공사"]
[{"$nulls":5},"광주교통공사"]
[{"$nulls":5},"세종도시교통공사"]
[{"$nulls":5},"경기교통공사"]
[{"$nulls":5},"국립공원공단"]